# Ludo Royale

Implementation & Process Plan

A phase-by-phase production playbook for a premium, modern, animated online multiplayer game

Target build value: $150,000-grade  ·  Android & iOS  ·  Unity  ·  2–8 players + teams + live voice

| Field | Detail |
| --- | --- |
| Product | Ludo Royale — online multiplayer Ludo (free, no ads, no real-money) |
| Platforms | Android 8+ and iOS 13+ (portrait, all-ages) |
| Engine | Unity 6.3 LTS (C#) |
| Scope | 2–8 players, FFA + teams (2v2/3v3/4v4), classic 4 / hex 6 / oct 8 boards, live voice, premium animation |
| Owner | premk |
| Version / Date | v1.0 · 27 June 2026 |
| Status | DRAFT for review — companion to the requirements & technical design document |

# Table of Contents

# 1. Executive Summary

This document turns the agreed Ludo Royale requirements into a concrete, sequential build plan: a set of 15 phases across 5 production stages that you can execute one at a time, each with a task checklist, clear deliverables, and a 'done' gate before moving on.

The ambition is explicit: build a game for modern, future-facing players — advanced animation, buttery-smooth play, and genuinely fun social sessions with friends over live voice. The plan is engineered to deliver a premium, ~$150,000-grade product, and §4 shows exactly how that investment maps to the work.

It follows the industry-standard pipeline — pre-production → production → alpha → beta → soft launch → live-ops — adapted for a real-time multiplayer mobile title, where a vertical-slice 'proof of fun' and a soft launch de-risk the big bets before full spend.

How to use it: work top-to-bottom. Don't start a phase until the previous phase's exit criteria are met. Phases 6–9 can run partly in parallel once their interfaces are fixed (noted in §6).

Companion document: the full game rules, architecture, data model and screen specs live in the requirements & technical design document in the repo's docs/ folder. This plan references it rather than repeating it.

# 2. The Vision & What Makes It a $150k-Grade Product

Vision: a Ludo that feels current — characters that walk and kick with personality, dice that land with weight and flair, transitions that glide, and friends laughing together over crystal-clear voice — all running smoothly on an ordinary phone and never broken by a dropped signal.

The premium bars we hold every phase to:

| Pillar | The bar (what 'premium' means here) |
| --- | --- |
| Animation & feel | Motion-artist-grade skeletal characters, 3D dice with slow-mo and particles, shared-element UI motion. 60 fps on mid devices, graceful 30 fps fallback on low-end. |
| Smoothness | Server-authoritative, < 200 ms perceived action latency, optimistic animation, and reconnect in under 2 seconds. |
| Social fun | Up to 8 friends, teams, live voice with team channels, emotes, and presence — the reasons people come back. |
| Fairness & trust | Server-rolled dice and validated moves — provably fair, cheat-resistant. |
| Reliability | Crash-free > 99.5%, tested across a real device matrix, no mid-match desyncs. |
| Inclusivity | Colour-blind-safe board, reduce-motion, text scaling, English + Hindi at launch. |

Cost reality check: at North-American studio rates a premium real-time multiplayer mobile game typically runs $250k–$1M+. This plan reaches the same production value for ~$150k by being capital-efficient — managed services (Photon/Agora/Firebase) instead of custom infrastructure, the Unity ecosystem instead of building from scratch, reuse of the design's already-defined animations, and an efficient blended team — not by cutting quality.

# 3. Production Approach & Methodology

Five stages map onto the standard six-stage pipeline and onto the 15 phases:

| Stage | Pipeline equivalent | Phases | Purpose |
| --- | --- | --- | --- |
| A — Pre-Production | Pre-production | 0 | Lock design + foundations |
| B — Production | Production | 1–9 | Build all features (rules → online → boards → social → voice → animation → meta) |
| C — Stabilization | Alpha + Beta | 10–11 | Feature-freeze, QA, content-lock, accessibility, closed beta |
| D — Launch | Launch (+ soft launch) | 12–13 | Soft launch to tune, then global release |
| E — Live-Ops | Post-launch live-ops | 14 | Patches, seasons, events, growth |

Working principles: milestone-based delivery with a definition-of-done gate per phase; a vertical slice to prove fun early; CI/CD from day one; analytics-informed tuning in soft launch; and a fallback MVP cut (2–4 players) held in reserve in case the 'full set before launch' timeline needs to flex.

# 4. Budget & Value Allocation ($150,000)

| Area | Allocation | Share | What it buys |
| --- | --- | --- | --- |
| Pre-production & design (Phase 0) | $9,000 | 6% | GDD, art bible, de-risk spikes, environment + CI |
| Core engineering — rules, online, resilience, extended boards (Phases 1–5) | $48,000 | 32% | The gameplay + netcode backbone |
| Backend, accounts, social & voice integration (Phases 6–7) | $21,000 | 14% | Identity, friends, matchmaking, live voice |
| Premium art & animation (Phase 8 + board art in Phase 5) | $36,000 | 24% | The differentiator: rigs, VFX, dice, board art |
| Meta systems & economy (Phase 9) | $9,000 | 6% | Store, currency, rewards, leaderboards |
| QA, testing, devices & security (Phases 10–11) | $15,000 | 10% | Structured QA + device lab + beta |
| Services & infrastructure (year 1) + tooling | $7,000 | 5% | Photon/Agora/Firebase, stores, asset licences |
| Contingency & project management | $5,000 | 3% | Risk buffer + coordination |
| TOTAL | $150,000 | 100% | A premium product built capital-efficiently |

Assumptions: an efficient blended team (e.g. India / Eastern-Europe senior rates), heavy use of managed-service free/low tiers, and Unity Asset Store leverage. Year-1 cloud/voice cost is modest under the free tiers and scales with active players, not installs; the soft launch (Phase 12) validates the live cost model before global scale.

# 5. Team & Roles

A lean core of 4–6 people delivers this scope; in a solo-led or outsourced model, roles combine and the calendar lengthens.

| Role | Focus | Active in phases |
| --- | --- | --- |
| Lead / Unity Gameplay Engineer | Rules core, client, animation integration, netcode | 1–10 |
| Multiplayer / Backend Engineer | Photon authority, Firebase, voice, infra, scaling | 3–7, 10, 12 |
| Game / UX Designer | GDD, screens, balance, economy, localisation | 0, 2, 9, 11 |
| Motion / VFX Artist (the premium hire) | Character rigs, animations, dice/capture VFX, board art | 5, 8, 11 |
| QA Engineer | Test plans, device matrix, automation, beta | 10–13 |
| Product / PM (part-time) | Planning, vendors, launch, live-ops | All |
| Audio (contract) | SFX and music | 7, 8 |

# 6. Timeline at a Glance

Sequential phase durations total roughly 12–16 months; with the parallel tracks below, a lean team realistically reaches global launch in ~10–12 months, then continuous live-ops.

Parallel tracks (after interfaces are fixed): the Motion/VFX artist works Phase 8 alongside engineering Phases 6, 7 and 9; QA tooling (Phase 10) ramps during Phase 8–9; store/marketing prep (Phase 11/13) begins during beta.

## Phase summary — the sequence to follow

| Phase | Title | Duration | Key outcome / gate |
| --- | --- | --- | --- |
| 0 | Discovery, Design Lock & Foundations | 3–4 wks | Signed GDD + art bible; CI build running on real Android & iOS devices |
| 1 | Core Rules Engine (Ludo.Core) | 3–4 wks | Engine-agnostic, 100%-tested rules; thousands of simulated games run clean |
| 2 | Playable Vertical Slice (offline, on-device) | 4–6 wks | A human finishes a polished 4-player game vs bots on a real phone — 'proof of fun' |
| 3 | Online Multiplayer (Server-Authoritative) | 4–6 wks | 2–4 players on separate devices play a fair, authoritative online match |
| 4 | Netcode Resilience & 'No-Disturbance' Layer | 3–4 wks | Drops recover in < 2 s; idle players auto-play; lag/exit/timeout all surfaced |
| 5 | Extended Boards & Team Modes (6 & 8 players) | 5–7 wks | A full 8-player 4v4 match completes online; HUD stays readable |
| 6 | Accounts, Friends & Backend | 4–5 wks | Log in, add a friend, invite to a private match, quick-match; logins/crashes hit the DB |
| 7 | Voice Chat & Audio | 3–4 wks | 8 players talk; mute/opt-out/report work; full SFX + music + haptics |
| 8 | Premium Animation & VFX — the signature look | 6–8 wks | Hits the full animation spec at 60/30 fps; 'wow' verified with test users |
| 9 | Meta Systems & Economy | 3–4 wks | Earn currency → buy & equip a cosmetic; daily streaks; leaderboards & ranked |
| 10 | Alpha — Feature-Complete & QA Hardening | 4–6 wks | Feature freeze; no P0/P1 bugs; crash-free > 99%; passes the device matrix |
| 11 | Beta — Content-Complete, Accessibility & Localization | 4–5 wks | Content locked; EN+HI + accessibility verified; store package + real beta feedback |
| 12 | Soft Launch (limited region) & Tuning | 4–6 wks | Retention / crash / latency / cost targets met in a real market |
| 13 | Global Launch | 2–3 wks + day-1 ops | Live worldwide on the App Store and Google Play; stable under launch load |
| 14 | Live-Ops, Growth & Iteration | Ongoing (15–25% of budget / yr) | A living product: steady patches, seasonal content, healthy retention & economics |

# 7. The Phased Plan (work through one phase at a time)

Each phase below lists its goal, an in-order task checklist, deliverables, the exit criteria that gate the next phase, and the premium quality bar it must clear.

# Stage A — Pre-Production

## Phase 0 — Discovery, Design Lock & Foundations

Duration: 3–4 wks    Outcome: Signed GDD + art bible; CI build running on real Android & iOS devices

Goal: Lock every open decision and stand up a professional development environment so we never rework foundations.

Tasks (work through in order):

- Resolve the 14 open questions in the requirements doc §17 into a signed decision log (voice vendor, backend, geometry, voice safety, extended-board art, currencies, ranked, login, languages, age policy, avatars).

- Finalise & sign off the Game Design Document (the existing requirements doc) as the v1 baseline.

- Produce the Art Bible / style guide: pastel design tokens, character (stickman) rig spec, full animation list, board-art spec including the 6- & 8-seat boards.

- Create vendor accounts and run small technical de-risk spikes: Unity 6.3 LTS, Photon Fusion, Agora/Photon Voice, Firebase.

- Set up the repo: Unity project skeleton, Git LFS for assets, branching model, coding standards, ScriptableObject GameConfig.

- Stand up CI/CD that produces signed Android (.aab) and iOS builds automatically.

- Set up project management: backlog, board, milestone schedule, risk register, cadence; define the QA strategy + device matrix.

Deliverables: Signed GDD + decision log, Art Bible, configured dev environment + CI/CD, project plan, risk register, spike results.

Exit criteria (Definition of Done): All §17 decisions locked; a 'hello-world' Unity build installs on a physical Android and iOS device via CI; team and tooling aligned.

Premium ($150k) quality bar: Foundations that won't need redoing — proper architecture, CI from day one, art direction locked before a line of gameplay art is made.

# Stage B — Production

## Phase 1 — Core Rules Engine (Ludo.Core)

Duration: 3–4 wks    Outcome: Engine-agnostic, 100%-tested rules; thousands of simulated games run clean

Goal: Build the deterministic, cheat-proof, fully unit-tested rules library that the whole game depends on — with no graphics or networking.

Tasks (work through in order):

- Implement parametric board geometry for 4/6/8 seats (ring = 13×N; constant ~56-step journey via HOME_ENTRY_OFFSET).

- Token states, legal-move generation, and a server-seeded RNG interface for dice.

- Capturing/kick-off, safe cells, blockades, exact-finish, three-sixes rule, and bonus-turn triggers.

- Team logic: 2v2/3v3/4v4 interleaved seating, shared turns, no teammate captures.

- Win/ranking resolution and abandonment handling.

- Auto-play AI heuristic with Easy/Medium/Hard tiers (also powers bots and idle takeover).

- Centralise all tunables in GameConfig.

- Write exhaustive unit tests for every rule + edge case, plus a headless simulator that plays thousands of games for balance and match-length stats.

Deliverables: Ludo.Core library, full unit-test suite, headless match simulator + balance report.

Exit criteria (Definition of Done): 100% rule coverage; thousands of simulated 2–8-player games complete without errors; match-length distribution acceptable.

Premium ($150k) quality bar: Provably fair, fully tested logic — the foundation that prevents an entire class of gameplay bugs and cheating later.

## Phase 2 — Playable Vertical Slice (offline, on-device)

Duration: 4–6 wks    Outcome: A human finishes a polished 4-player game vs bots on a real phone — 'proof of fun'

Goal: Produce ONE polished, representative slice (classic 4-seat) that proves the game is fun and hints at the premium look — before scaling.

Tasks (work through in order):

- Build the Unity board scene (classic 4-seat), camera and touch input.

- Tap-to-roll → dice (first-pass animation); token rendering and cell-to-cell movement.

- Wire the UI/view-model to Ludo.Core; render purely from state diffs.

- Hot-seat + bots for a full local 4-player game.

- First-pass stickman walk and a basic capture; first-pass SFX and haptics.

- Performance pass on a low-end Android device.

Deliverables: On-device vertical slice (4-player classic vs bots) with validated feel and look.

Exit criteria (Definition of Done): A human completes a 4-player game vs bots on a physical device; the slice feels good; 60 fps mid / 30 fps low-end.

Premium ($150k) quality bar: The vertical-slice gate: if it isn't delightful here, we iterate before building everything else on top of it.

## Phase 3 — Online Multiplayer (Server-Authoritative)

Duration: 4–6 wks    Outcome: 2–4 players on separate devices play a fair, authoritative online match

Goal: Make it real-time and online with the server as the referee — the integrity backbone (anti-cheat) even though the game is free.

Tasks (work through in order):

- Integrate Photon Fusion in server/host authoritative mode.

- Move Ludo.Core to the authority; clients send intents only.

- Server-side RNG dice; server validates every move and rejects illegal ones.

- State sync (snapshots + deltas) and a server-side turn timer.

- Lobby/room join for 2–4 players; basic matchmaking stub.

- Optimistic dice animation reconciled with the authoritative result.

Deliverables: Online 2–4 player matches with verified anti-cheat.

Exit criteria (Definition of Done): Four players on separate devices complete a match; tampered/illegal moves are rejected; median move-confirm < 200 ms.

Premium ($150k) quality bar: Fair, authoritative, responsive — the trust layer that cheap clones skip.

## Phase 4 — Netcode Resilience & 'No-Disturbance' Layer

Duration: 3–4 wks    Outcome: Drops recover in < 2 s; idle players auto-play; lag/exit/timeout all surfaced

Goal: Survive real mobile networks gracefully — the single biggest driver of 'smooth gameplay without disturbance' (reqs #2, #7).

Tasks (work through in order):

- Reconnect/resume within a grace window via full StateSync rejoin.

- Connectivity detection by heartbeat (not just the radio); 'Reconnecting…' banners.

- Per-seat lag indicators; regional routing/pinning.

- 60 s turn timer with warnings + system auto-play (heuristic) + AFK handling.

- Graceful exit/quit → bot takeover; abandonment handling.

- Non-blocking toast/notification system (port the design's toastIn).

Deliverables: Complete resilience and notifications layer.

Exit criteria (Definition of Done): Forced disconnects recover < 2 s; idle seats auto-play; lag/exit/timeout all visible; multi-hour soak test stable.

Premium ($150k) quality bar: 'No disturbance' delivered — the thing players actually notice and that competitors get wrong.

## Phase 5 — Extended Boards & Team Modes (6 & 8 players)

Duration: 5–7 wks    Outcome: A full 8-player 4v4 match completes online; HUD stays readable

Goal: Ship the headline differentiator — up to 8 players and 2v2/3v3/4v4 teams on bespoke boards.

Tasks (work through in order):

- Produce hexagonal (6-seat) and octagonal (8-seat) board art in the pastel style (the §14.4 design gap).

- Integrate the parametric boards into rendering; verify geometry against Ludo.Core.

- Team-setup UI (2v2/3v3/4v4), interleaved seating, team rules, shared turns.

- Up-to-8-player HUD layout (avatars, mic, turn, lag) without crowding.

- Online testing at 6 and 8 players; balance and match-length tuning.

Deliverables: Full 6/8-player and team online play.

Exit criteria (Definition of Done): An 8-player 4v4 match completes online; HUD is readable; match length is acceptable.

Premium ($150k) quality bar: A feature most Ludo apps simply don't have — executed cleanly, not bolted on.

## Phase 6 — Accounts, Friends & Backend

Duration: 4–5 wks    Outcome: Log in, add a friend, invite to a private match, quick-match; logins/crashes hit the DB

Goal: Identity, the social graph, matchmaking, and the backend logging you asked for.

Tasks (work through in order):

- Firebase Auth (Apple / Google / Guest) and the onboarding screens.

- Profile/Stats and the backend schema (users, friends, matches, participants, auth_events, sessions, crash_logs, reports).

- Friends + presence + invites (codes/deep links); private rooms; quick matchmaking by mode/region with bot-fill.

- Crash logging (Crashlytics) + auth/session logging; push (FCM/APNs) for turn and invite notifications.

Deliverables: Login, friends, matchmaking, private rooms, logging and push.

Exit criteria (Definition of Done): Log in, add a friend, invite to a private match, and quick-match all work; crashes and logins are recorded in the DB.

Premium ($150k) quality bar: Frictionless social — 'play with friends' actually works end to end.

## Phase 7 — Voice Chat & Audio

Duration: 3–4 wks    Outcome: 8 players talk; mute/opt-out/report work; full SFX + music + haptics

Goal: Live voice and a complete audio experience — the core of 'more fun with friends' (req #5).

Tasks (work through in order):

- Integrate Agora / Photon Voice; match room + team sub-channels.

- Controls: join/leave (full opt-out), mic push-to-talk/open toggle, per-player mute + volume, OS audio routing.

- Speaking indicators (pulseRingV) and mic badges; consent + permissions; friends-only-voice option; Report flow.

- SFX pass (dice, hop, kick, home, win, UI), music beds with ducking under voice, and haptics.

Deliverables: 8-player voice with controls and safety, plus the full audio layer.

Exit criteria (Definition of Done): Eight players can talk; mute, opt-out and report work; audio mixes cleanly with voice.

Premium ($150k) quality bar: Real social presence and store-compliant safety — not an afterthought.

## Phase 8 — Premium Animation & VFX — the signature look

Duration: 6–8 wks    Outcome: Hits the full animation spec at 60/30 fps; 'wow' verified with test users

Goal: Deliver the visual wow that justifies the premium positioning and makes the game feel modern and advanced (reqs #3, #6, #8, #9).

Tasks (work through in order):

- Full skeletal character rig (Spine/DragonBones): idle/breathe, walk (legF/legB/armF/armB/walkBob/hop), jump, the kick-off sequence (lgWindup→lgKicker→lgKickLeg→lgPow/powPop, victim koFly), celebrate/wave, win/lose — ported from the design keyframes.

- Avatar-skinning system (personalised 'Prem'-style avatars + a preset roster) over a shared skeleton.

- Premium dice: 3D physics tray with slow-mo + particles (sprite fallback on low-end), legal-move telegraphing, special 6/bonus FX.

- Capture screen-shake, dust and speed-lines; board ambience, safe-cell shimmer/starSpin, turn-glow; floating emotes.

- UI/transition motion (shared-element), the radial turn timer, confetti win sequence.

- Device-tier graphics scaling and a performance/thermal pass.

Deliverables: The complete animation/VFX set hitting the spec across device tiers.

Exit criteria (Definition of Done): Matches §8 of the GDD; 60 fps high/mid and 30 fps low-end; 'wow' confirmed with test users.

Premium ($150k) quality bar: THE differentiator — motion-artist-grade juice and console-grade feel. This phase carries the largest art investment.

## Phase 9 — Meta Systems & Economy

Duration: 3–4 wks    Outcome: Earn currency → buy & equip a cosmetic; daily streaks; leaderboards & ranked

Goal: The modern retention loop — store, currencies, rewards, leaderboards — all free.

Tasks (work through in order):

- Store of free cosmetics (token/dice/board skins, characters, emotes) with unlocking.

- Coins + gems economy, earned-only, with server-validated sources/sinks and anti-abuse.

- Daily Rewards (streaks); Leaderboards + Tournaments (e.g. Weekend Cup); ranked points/MMR.

- Profile achievements and cosmetic equipping.

Deliverables: The full meta/retention loop.

Exit criteria (Definition of Done): Earn currency, buy a cosmetic, equip it; daily streak works; leaderboard and ranked update correctly.

Premium ($150k) quality bar: Contemporary engagement systems — depth without any monetisation pressure.

# Stage C — Stabilization (Alpha & Beta)

## Phase 10 — Alpha — Feature-Complete & QA Hardening

Duration: 4–6 wks    Outcome: Feature freeze; no P0/P1 bugs; crash-free > 99%; passes the device matrix

Goal: Everything is in — now make it genuinely stable.

Tasks (work through in order):

- Feature freeze, then structured QA: functional, regression, compatibility (device matrix), performance, network/soak, security/anti-cheat, voice moderation.

- Wire automated tests into CI; run a disciplined bug-triage-and-fix loop.

- Load/scale test many concurrent matches; monitor realtime/voice cost.

Deliverables: A stable alpha build.

Exit criteria (Definition of Done): No P0/P1 bugs; crash-free sessions > 99%; passes the device matrix; load test holds.

Premium ($150k) quality bar: Reliability — premium products don't crash or desync.

## Phase 11 — Beta — Content-Complete, Accessibility & Localization

Duration: 4–5 wks    Outcome: Content locked; EN+HI + accessibility verified; store package + real beta feedback

Goal: Lock final content, make it inclusive, and validate with real users.

Tasks (work through in order):

- Lock final art/audio; localise (English + Hindi), RTL-ready structure.

- Accessibility: colour-blind-safe palette + secondary token cues, text scaling, reduce-motion, mono audio.

- Privacy policy, age-gate/consent, store age ratings; store assets (screenshots, trailer, descriptions, ASO).

- Closed beta (TestFlight / Play closed track) with real users; analytics tuning; data-driven balance.

Deliverables: Beta build, content locked, store-submission package, beta-feedback report.

Exit criteria (Definition of Done): Beta KPIs acceptable; localisation and accessibility verified; store assets ready.

Premium ($150k) quality bar: Polished, inclusive, and validated by real players — not just the team.

# Stage D — Launch

## Phase 12 — Soft Launch (limited region) & Tuning

Duration: 4–6 wks    Outcome: Retention / crash / latency / cost targets met in a real market

Goal: De-risk the global launch with real-world data before scaling spend and servers.

Tasks (work through in order):

- Release to a limited region (or a small % rollout); monitor crashes, D1/D7 retention, latency, match fill, and voice/infra cost.

- Tune matchmaking, balance, economy and onboarding from data; scale infrastructure; add cost guardrails (e.g. voice kill-switch).

Deliverables: Validated KPIs + confirmed cost model and a tuned build.

Exit criteria (Definition of Done): Retention, crash, latency and cost targets are met; ready to scale.

Premium ($150k) quality bar: Data-driven confidence rather than hope.

## Phase 13 — Global Launch

Duration: 2–3 wks + day-1 ops    Outcome: Live worldwide on the App Store and Google Play; stable under launch load

Goal: Ship it to the world with a monitored, confident launch.

Tasks (work through in order):

- Build the release candidate; submit to Apple and Google and pass certification.

- Prepare marketing assets, launch plan, ASO and community channels.

- Run a day-1 war-room: monitoring, on-call, hotfix readiness.

Deliverables: Live on both stores globally.

Exit criteria (Definition of Done): Approved and live on both stores; stable under launch-day load.

Premium ($150k) quality bar: A calm, instrumented launch — not a scramble.

# Stage E — Live-Ops

## Phase 14 — Live-Ops, Growth & Iteration

Duration: Ongoing (15–25% of budget / yr)    Outcome: A living product: steady patches, seasonal content, healthy retention & economics

Goal: Keep the game alive, fresh and growing after launch.

Tasks (work through in order):

- Regular patch cadence, crash/ANR triage, and balance updates.

- Seasonal content: new boards, skins, characters, tournaments and events.

- Analytics-driven iteration (retention/funnel), community management, A/B testing.

- Continuous infrastructure cost optimisation at scale.

Deliverables: A live-ops calendar and an ongoing release train.

Exit criteria (Definition of Done): No exit — this is steady-state operation with healthy retention and stable unit economics.

Premium ($150k) quality bar: A product that keeps players coming back, not a one-shot release.

# 8. Quality, Testing & Acceptance

Definition of Done (every phase): code reviewed; unit/integration tests passing in CI; runs within the performance budget on the device matrix; no open P0/P1 bugs; visual parity with the Art Bible; analytics events instrumented.

Test types used in Stage C: functional, regression, compatibility (device matrix), performance/thermal, network/soak (drops, lag, reconnect), load/scale (many concurrent matches), security/anti-cheat, and voice moderation.

| Performance budget | Target |
| --- | --- |
| Frame rate | 60 fps high/mid; ≥ 30 fps low-end; never < 30 during dice/capture |
| Perceived action latency | Dice tumble < 50 ms (optimistic); authoritative confirm < 200 ms median |
| Reconnect / resume | < 2 s after network returns (90 s grace window) |
| Cold start | < 4 s to home on mid devices |
| Install size | Base < 150 MB (Addressables for extra boards/skins) |
| Device matrix | Android 8+ from 2–3 GB-RAM phones up; iOS 13+ across recent iPhones/iPads |

# 9. Success Metrics (KPIs)

| Metric | Launch target | Why it matters |
| --- | --- | --- |
| Crash-free sessions | > 99.5% | Stability / premium feel |
| D1 / D7 retention | > 40% / > 18% | Casual board-game benchmarks |
| Quick-match start time | < 10 s | Frictionless matchmaking |
| Median move-confirm latency | < 200 ms | Responsiveness |
| Reconnect success rate | > 95% | Resilience on mobile networks |
| Voice quality (MOS) | Good / clear | Social experience |
| Store rating | > 4.4 stars | Perceived quality |

# 10. Risk Management

| Risk | Impact | Mitigation |
| --- | --- | --- |
| 'Full feature set before launch' lengthens time-to-market | High | Phased plan + a 2–4-player MVP cut kept ready as a fallback launch |
| 8-player + voice cost on a no-revenue app | Med-High | Push-to-talk, region pinning, bots for idle seats, voice kill-switch, CCU/minute monitoring |
| Extended-board art (6/8-seat) not in current design | Med | Commission/produce hex+oct art early in Phase 5; lock the spec in Phase 0 |
| Premium animation schedule slips | Med | Lock the keyframe list in the Art Bible; reuse the design's defined animations; device-tier fallbacks |
| Store certification / age-rating delays | Med | Prepare privacy, age-gate and assets in Phase 11; submit early in Phase 13 |
| Voice moderation / abuse (store policy) | Med | Per-user mute + Report + friends-only-voice default + age gate |
| Infra cost spike on viral success | Med | Managed services that scale by CCU; autoscale + cost guardrails; soft-launch cost validation |

# 11. Immediate Next Actions

- Decide the open questions — answer the 14 items in requirements §17 so the spec is final (I can walk you through them).

- Approve this plan — confirm the phases, budget split and timeline (or tell me what to adjust).

- Greenlight Phase 0 — on approval I scaffold the Unity 6.3 project, repo structure, CI/CD and the Ludo.Core skeleton.

- Choose extended-board art production — commission an artist vs AI-assisted generation for the hex/oct boards, in the pastel style.

- Confirm the team model — in-house, outsourced, or solo-led — so the calendar and budget are tuned to reality.

# 12. Appendix

## A. Technology stack (summary)

| Layer | Choice | Role |
| --- | --- | --- |
| Engine | Unity 6.3 LTS (C#) | Client, rendering, animation, physics |
| Rules core | Ludo.Core (pure C#) | Engine-agnostic, unit-tested gameplay logic |
| Realtime / authority | Photon Fusion 2 (server/host) | Authoritative match, dice, validation, sync |
| Backend | Firebase (Auth, Firestore, Functions, Crashlytics, FCM) | Identity, friends, logging, push |
| Voice | Agora Voice (or Photon Voice) | Match + team voice channels |
| Animation | Spine / DragonBones + DOTween + VFX Graph | Skeletal characters, dice, captures, UI motion |

## B. Research sources

Production pipeline and cost benchmarks referenced in this plan:

- Magic Media — 7 stages of the game development pipeline

- Game-Ace — Game development stages: idea to launch

- Zco — Complete guide to mobile game development (2026)

- NGS — Mobile game development cost breakdown

- Capermint — Mobile game development costs (2025)

## C. Companion document

Full requirements, game-rules engine, architecture, data model and the 10-screen design system: see docs/Ludo-Game-Design-and-Technical-Requirements.md and the imported design under design/.